## Task List
Task | Description | Owner | Prerequisites | Estimated Duration
Prep Hosts | Install Windows Server on HostA & HostB | Systems Admin | Hardware or VM infra | 2 hrs
Join Domain | Add hosts to Active Directory | Systems Admin | AD Domain up | 15 min
Install Roles | Install Hyper-V + Failover Clustering | Systems Admin | Domain joined | 30 min
Configure NICs | Assign static IPs for mgmt & cluster traffic | Systems Admin | Network plan | 15 min
Enable iSCSI | Configure iSCSI initiator for shared storage | Storage Admin | iSCSI target available | 30 min
Validate Cluster | Run Test-Cluster validation | Cluster Admin | Shared storage online | 20 min
Create Cluster | Run New-Cluster PowerShell or GUI | Cluster Admin | Validation complete | 15 min
Add CSV | Add disk to cluster and convert to CSV | Cluster Admin | Disk online & unformatted | 15 min
Create VMs | Create VMs from config plan | Virtualization Admin | Cluster + CSV ready | 1–2 hrs
Install OS | Mount ISO & configure VMs | Systems Admin | VMs created | 1–2 hrs
Add to Cluster | Use Add-ClusterVirtualMachineRole | Cluster Admin | OS installed (optional) | 15 min
Anti-Affinity | Create and apply anti-affinity rules | Cluster Admin | VMs clustered | 10 min
Test Failover | Simulate node outage / Live Migration | Cluster Admin | Full deployment | 30 min

## CSV Setup Guide
Step | Action
Provision iSCSI Target | Create LUN and assign IQN access to Hyper-V hosts
Connect to Target | Use PowerShell New-IscsiTargetPortal and Connect-IscsiTarget
Initialize Disk | Set offline disk online, initialize and format it as NTFS
Add Disk to Cluster | Use Get-ClusterAvailableDisk and Add-ClusterDisk
Convert to CSV | Use Add-ClusterSharedVolume
Access CSV | Verify path C:\ClusterStorage\Volume1 available from all nodes
Test CSV Access | Create dummy file from each node and validate shared access